## v1
Section/Use Case |  |  | Date Verified | Comments
Requirement
Deployment
|  | Build and distribute through TestFlight | 2017-06-24
Navigation/General
|  | Runs on iPhone | 2017-06-06
|  | Runs on iPad | 2017-06-07 | Yes, but it (I used an iPad Pro [12.9 inch]) may not meet all the same requirements as the iPhone. I tested the requirements on an iPhone 7. For example, on the iPad, the first view on app open is the content from the account tab but without the tabs on the bottom. Roger: added Show login... requirement; accepted this requirement as verified.
|  | Runs on iPhone in portrait mode | 2017-06-06
|  | Runs on iPad in portrait mode | 2017-06-06
|  | Runs on iPad in landscape mode | 2017-06-06
|  | App icon | 2017-06-06
|  | Loading image | 2017-06-06
|  | Show login/signup/skip option until first successful login, successful signup, or skip | 2017-06-07 | Verified by Kevoye
Navigation tabs
|  | Home | 2017-06-06
|  | Controller | 2017-06-06
|  | History | 2017-06-06
|  | Account | 2017-06-06
|  | Fails gracefully when cannot connect to server | 2017-06-06
|  | Terms & Conditions on sign-up page | 2017-06-06
Home
|  | Shown on home tab | 2017-06-06
|  | The first view on app open | 2017-06-06
|  | Input device ID | 2017-06-06
|  | Button to view most-recent-cook on input device ID | 2017-06-06
|  | Handle invalid device ID | 2017-06-07 | Yes, but "1234567890" results in an error: "https://myflameboss.com/api/v1/devices/123456890: status 404" Accepted with issue added for API
|  | Use user-assigned names for controllers | 2017-06-06
|  | View added-controllers most recent cooks | 2017-06-06
|  | View local-network most recent cooks | 2017-06-07 | N/A -- I don't have any local controllers. Verified by Kevoye
|  | View added-controllers before local-network | 2017-06-06
|  | Cook list entries nav to view cook | 2017-06-06
|  | If cook has ended, entry starts with date formatted like: JUN 03 FRI 8:17AM - 4:00PM | 2017-06-14
|  | If cook has not ended, date is formatted like: JUN 03 FRI 8:17AM | 2017-06-14
Add a controller
|  | Input Device ID | 2017-06-06
|  | Input PIN | 2017-06-06
|  | Input SN (optional) | 2017-06-14 | N/A -- I don't have an SN to use for testing.
Controller settings
Controller name
|  | Easy to find in navigation | 2017-06-06
|  | Input name | 2017-06-06
Wifi settings
Manual wifi settings
|  | Input SSID (not shown in choices from controller) | 2017-06-06 | This can be inputted, but it doesn't persist when returning to this view. Roger: Accepted with redmine issue added against API which includes re-verifying the iPhone app.
|  | Input password, hidden | 2017-06-12 | Password isn't hidden. Roger: Fixed.
|  | Input wifi security type | 2017-06-06
Sound
|  | Change sound setting | 2017-06-07
|  | No sound, chirps only, or chirps and alarms | 2017-06-06
|  | Edit controller name | 2017-06-06
Account
Sign up
|  | Input email | 2017-06-06
|  | Input email with email keypad | 2017-06-07 | The regular keyboard is shown. Roger: saw email keyboard with @ symbol
|  | Input username | 2017-06-06
|  | Input username default lowercase | 2017-06-06
|  | Default temperature scale by device locale | 2017-06-06
Login
|  | Use email or username | 2017-06-06
|  | Secure password entry | 2017-06-06
|  | Handle incorrect pw | 2017-06-06
|  | Logout | 2017-06-06
View/edit user profile
|  | View username | 2017-06-06
|  | View email | 2017-06-06
|  | View preferred temp scale | 2017-06-06
|  | Change email | 2017-06-07 | It says that a confirmation email was sent, but I never received it. Roger: accepted with issue against API
|  | Use email keypad for email input | 2017-06-07 | The regular keyboard is shown. Roger: saw keypad with @ symbol
|  | Change preferred temp scale | 2017-06-06
View cook
|  | Back control navigates to previous view | 2017-06-06
|  | User-assigned title used if set | 2017-06-06
|  | View pit temp, meat temps, and blower output | 2017-06-06
|  | View graph of temps and blower output over time | 2017-06-06
|  | Share on twitter | 2017-06-07 | This is not an option when the share dialog pops up. Roger: observed on real device if twitter is installed
|  | Share on facebook | 2017-06-07 | This is not an option when the share dialog pops up. Roger: observed on real device if facebook is installed
|  | View set temp | 2017-06-06
|  | Change set temp | 2017-06-07 | This can be inputted, but the change isn't reflected in the previous view or when returning to this view to change it.
|  | Show valid range for set temp | 2017-06-07 | Roger verified
|  | Show pit alarm enabled setting | 2017-06-12
|  | Show pit alarm difference limit | 2017-06-12
|  | Change pit alarm enabled setting | 2017-06-07 | This can be inputted, but the change isn't reflected in the previous view or when returning to this view to change it.
|  | Show valid range for pit alarm difference limit | 2017-06-07
|  | View meat alarm done temp | 2017-06-12
|  | Change meat alarm done temp | 2017-06-12 | This can be inputted, but the change isn't reflected in the previous view or when returning to this view to change it. Roger: Fixed
|  | Validate input meat alarm done temp range | 2017-06-12 | No feedback is given regardless of what is entered. Roger: behavior accepted for v1
|  | View meat alarm warm temp | 2017-06-06
|  | Change meat alarm warm temp | 2017-06-14 | This can be inputted, but the change isn't reflected in the previous view or when returning to this view to change it. Roger: updates are being shown now
|  | Validate input meat alarm warm temp range | 2017-06-14 | No feedback is given regardless of what is entered. Roger: feedback added
Edit cook information
|  | Change cook name | 2017-06-14 | Yes, but only on previous cook that is no longer active. Otherwise, when I try to type in something, the field keeps reseting and erasing what I type (maybe because the cook information is being refreshed every few seconds). Roger: Issue fixed
|  | Change notes | 2017-06-14 | Yes, but only on previous cook that is no longer active. Otherwise, when I try to type in something, the field keeps reseting and erasing what I type (maybe because the cook information is being refreshed every few seconds). Roger: Issue fixed
View cook history
|  | If cook has ended, entry starts with date formatted like: JUN 03 FRI 8:17AM - 4:00PM | 2017-06-14
|  | If cook has not ended, date is formatted like: JUN 03 FRI 8:17AM | 2017-06-14
|  | Title is cook title if set by user | 2017-06-14 | Yes, but it also shows when the cook began/ended above, and the date format is incorrect. It shows the begin date only (not end date also) and then a time range, such as "MAY 13 SAT 7:09PM - 7:09PM" when it should indicate that the cook was "MAY 13 SAT 7:09PM - MAY 14 SUN 7:09PM." ***Note: In my opinion, I think it is better to include the date/time range above like it is currently implemented (although correctly with the end date, not just the begin date). Roger: modified requirements
|  | Otherwise if controller name is set by user: Cook # on user-controller-name | 2017-06-14 | Yes, but it shows the begin date only (not end date also) and then a time range, such as "MAY 09 TUE 7:08PM - 7:08PM Cook 89531 on Controller 8838" when it should indicate that the cook was "MAY 09 TUE 7:08PM - MAY 10 WED 7:08PM on My Awesome Controller." Roger: modified requirements
|  | Otherwise Cook # on Controller # | 2017-06-14 | Yes, but it shows the begin date only (not end date also) and then a time range, such as "MAY 09 TUE 7:08PM - 7:08PM Cook 89531 on Controller 8838" when it should indicate that the cook was "MAY 09 TUE 7:08PM - MAY 10 WED 7:08PM on Controller 8838." Roger: modified requirements
|  | Ordered by date most recent first | 2017-06-06
|  | Offer way to delete cooks | 2017-06-06
|  | Nav to view cook | 2017-06-06
Receive notices
|  | New cook started | 2017-06-14 | N/A -- I can't test this.
|  | Pit temp alarm is active (pit temp near set temp) | 2017-06-14
|  | Pit temp out of normal range | 2017-06-14 | N/A -- I can't test this.
|  | Meat done | 2017-06-14 | N/A -- I can't test this.
|  | User added controller | 2017-06-14 | N/A -- I can't test this.
|  | Above when app is in foreground | 2017-06-14
|  | Above when app is in background | 2017-06-14
|  | Above when app is terminated | 2017-06-14

## v1.4
Section/Use Case |  |  | Date Verified | Comments | Date Reverified | Comments
Requirement
Deployment
|  | Build and distribute through TestFlight | 2017-09-05 | RC: Deleted | x
Navigation/General
|  | Runs on iPhone | 2017-08-30 |  | 2017-10-19
|  | Runs on iPad | 2017-08-30 |  | 2017-10-19
|  | Runs on iPhone in portrait mode | 2017-08-30 |  | 2017-10-19
|  | Runs on iPhone in landscape mode | 2017-09-05 | RC: Deleted | x
|  | Runs on iPad in portrait mode | 2017-08-30 |  | 2017-10-19
|  | Runs on iPad in landscape mode | 2017-08-30 |  | 2017-10-19 | Issue 566 - Controller image in Connect screens look stretched out
|  | App icon | 2017-08-30 |  | 2017-10-19
|  | Loading image | 2017-08-30 |  | 2017-10-19
|  | Show login/signup/skip option until first successful login, successful signup, or skip | 2017-08-30 |  | 2017-10-19
|  | Show phone offline state when phone cannot communicate with server or controller |  | Issue 438 |  | Issue 438
Navigation tabs
|  | Home | 2017-08-30 |  | 2017-10-19
|  | Controller | 2017-08-30 |  | 2017-10-19
|  | History | 2017-08-30 |  | 2017-10-19
|  | Account | 2017-08-30 |  | 2017-10-19
|  | Fails gracefully when cannot connect to server |  | Unable to test |  | Unable to test
|  | About? |  | RC: add issue - Haley to design |  | Added Issue 563
|  | Terms & Conditions | 2017-08-30 |  | 2017-10-19
|  | Link to https://www.FlameBoss.com |  | RC: add to About issue |  | Added Issue 563
|  | Link to web app myflameboss.com |  | RC: add to About issue |  | Added Issue 563
|  | Link to Facebook page |  | RC: add to About issue |  | Added Issue 563
Home
|  | Shown on home tab | 2017-08-31 |  | 2017-10-19
|  | The first view on app open | 2017-08-31 |  | 2017-10-19
|  | Input device ID | 2017-08-31 |  | 2017-10-19
|  | Button to view most-recent-cook on input device ID | 2017-08-31 |  | 2017-10-19
|  | Handle invalid device ID | 2017-08-31 | Error message needs to be more specific |  | Issue 314
|  | Handle no-cook-yet on valid device ID | 2017-08-31 |  | 2017-10-19
|  | Use user-assigned names for controllers | 2017-08-30 |  |  | Issue 570 - Controller name disappears when user assigns a cook name
|  | View added-controllers most recent cooks | 2017-08-30 |  | 2017-10-19
|  | View local-network most recent cooks | 2017-08-30 |  | 2017-10-19
|  | View added-controllers before local-network | 2017-08-30 |  | 2017-10-19
|  | Cook list entries nav to view cook | 2017-08-30 |  | 2017-10-19
|  | If end time is on next day, add (+1 day) like: JUN 03 FRI 8:17AM - 4:00PM (+1 day) |  | RC: add issue | 2017-10-19 | Issue 439 - Delivery
Setup wifi with AP mode
|  | Popup dialog to start if no devices in index (either IP or added) |  |  |  | Added Issue 567
|  | Can also start from controllers tab |  |  | 2017-10-19
|  | Wizard style steps |  |  | 2017-10-19
|  | Cancellation/abort available at any time |  |  | 2017-10-19
|  | Instructs to put controller in AP Mode |  |  | 2017-10-19
|  | Instructs to join controller network |  |  | 2017-10-19
|  | Instructs to re-open app |  |  | 2017-10-19
|  | Shows when connected to Flame Boss |  |  | 2017-10-19
|  | Shows networks visible to controller for selection |  |  | 2017-10-19
|  | Inputs password, hidden by default |  |  | 2017-10-19
|  | Show password option |  |  |  | Added Issue 568
|  | App detects controller online |  | RC: add feature issue |  | Added Issue 569
|  | Instructs to find PIN on controller |  |  |  | Added Issue 569
|  | Inputs PIN |  |  |  | Added Issue 569
|  | Adds controller to users profile |  |  |  | Added Issue 569
Add a controller
|  | Input Device ID | 2017-08-30 |  | 2017-10-19
|  | Input PIN | 2017-08-30 |  | 2017-10-19
|  | Input SN (optional) | 2017-08-30 |  | 2017-10-19
|  | Validate SN is 6 or 7 digit number |  | RC: add issue | 2017-10-19 | Issue 446 - Delivery
Controller settings
Controller name
|  | Easy to find in navigation | 2017-08-30 |  | 2017-10-19
|  | Input name | 2017-08-30 |  | 2017-10-19
Wifi settings
Scanned wifi settings
|  | Easy to find in navigation | 2017-09-05 | RC: deleted | x
|  | View SSID | 2017-09-05 | RC: deleted | x
|  | View security type | 2017-09-05 | RC: deleted | x
|  | Cannot view password | 2017-09-05 | RC: deleted | x
|  | SSID choices from controller | 2017-09-05 | RC: deleted | x
|  | Input password, hidden by default | 2017-09-05 | RC: deleted | x
|  | Show password option (while inputting) | 2017-09-05 | RC: deleted | x
Manual wifi settings
|  | Input SSID (not shown in choices from controller) | 2017-08-30 |  | 2017-10-19
|  | Input password, hidden by default | 2017-09-05 |  | 2017-10-19
|  | Show password option (while inputting) | 2017-09-05 | RC: deleted | x
|  | Input wifi security type | 2017-08-30 |  | 2017-10-19
Sound
|  | View current sound setting | 2017-09-05 |  | 2017-10-19
|  | Change sound setting | 2017-08-30 |  | 2017-10-19
|  | No sound, chirps only, or chirps and alarms | 2017-08-30 |  | 2017-10-19
|  | Edit controller name | 2017-08-30 |  | 2017-10-19
Account
Sign up
|  | Input email | 2017-08-30 |  | 2017-10-19
|  | Input email with email keypad | 2017-08-30 |  | 2017-10-19
|  | Input username | 2017-08-30 |  | 2017-10-19
|  | Input username default lowercase | 2017-08-30 |  | 2017-10-19
|  | Input phone | 2017-09-05 | Removed | x
|  | Input phone with phone keypad | 2017-09-05 | Removed | x
|  | Input texts notices enabled | 2017-09-05 | Removed | x
|  | Input temperature scale | 2017-08-30 |  | 2017-10-19
|  | Default temperature scale by device locale |  | Unable to test RC: iPhone Settings -> General -> Language & Region; change to Europe; sign up; should see Celsius | 2017-10-19
Login
|  | Use email or username | 2017-08-30 |  | 2017-10-19
|  | Secure password entry | 2017-08-30 |  | 2017-10-19
|  | Handle incorrect pw | 2017-08-30 |  | 2017-10-19
|  | Handle lockout too many tries |  | I was able to log in the 27th time after 26 attempts with the wrong password. RC: add issue |  | Added Issue 565
|  | Logout | 2017-08-30 |  | 2017-10-19
View/edit user profile
|  | View username | 2017-08-30 |  | 2017-10-19
|  | View email | 2017-08-30 |  | 2017-10-19
|  | View mobile phone number | x | Removed for this release | x
|  | View text confirmation status of phone number | x | Removed for this release | x
|  | Input text confirmation code only if we sent a code and it is not confirmed yet | x | Removed for this release | x
|  | View texts enabled option | x | Removed for this release | x
|  | View preferred temp scale | 2017-08-30 |  | 2017-10-19
|  | Change email | 2017-08-30 |  | 2017-10-19
|  | Validate email | 2017-08-30 |  | 2017-10-19
|  | Use email keypad for email input | 2017-08-30 |  | 2017-10-19
|  | Change mobile phone number | x | Removed for this release | x
|  | Validate mobile phone number | x | Removed for this release | x
|  | Use keypad for phone number input | x | Removed for this release | x
|  | Change texts enabled option | x | Removed for this release | x
|  | Change preferred temp scale | 2017-08-30 |  | 2017-10-19
View cook
|  | Back control navigates to previous view | 2017-08-30 |  | 2017-10-19
|  | User-assigned title used if set | 2017-08-30 |  | 2017-10-19
|  | View pit temp, meat temps, and blower output | 2017-08-30 |  | 2017-10-19
|  | View graph of temps and blower output over time | 2017-08-30 |  | 2017-10-19
Share link for myflameboss.com
|  | Share on twitter | 2017-08-30 |  | 2017-10-19
|  | Reference Flame Boss's twitter username | 2017-09-05 |  | 2017-10-19
|  | Share on facebook | 2017-08-30 |  | 2017-10-19
|  | Reference Flame Boss's facebook username |  | RC: run by Jeff to see priority of this |  | See previous comment
|  | View set temp | 2017-08-30 |  | 2017-10-19
|  | Change set temp | 2017-08-30 |  | 2017-10-19
|  | Show valid range for set temp | 2017-08-30 |  | 2017-10-19
|  | Validate input set temp range: on error, show (again) range required, allow cancel |  | RC: added back; needs verification | 2017-10-19
|  | Show activity indicator until response from server, timeout 10 sec: change phone to offline |  | See issue #438 Add issue for Set button disappearing |  | Issue 438 Issue 440 - Delivery status for set button disappearing; unable to reproduce
|  | View pit alarm | 2017-08-30 |  | 2017-10-19
|  | Change pit alarm | 2017-08-30 |  | 2017-10-19
|  | Validate input pit alarm range: on error, show (again) range required, allow cancel |  | RC: added back; needs test | 2017-10-19
|  | View meat alarm done temp | 2017-08-30 |  | 2017-10-19
|  | Change meat alarm done temp | 2017-08-30 |  | 2017-10-19
|  | Validate input meat alarm done temp range | 2017-08-30 |  | 2017-10-19
|  | View meat alarm warm temp | 2017-08-30 |  | 2017-10-19
|  | Change meat alarm warm temp | 2017-08-30 |  | 2017-10-19
|  | Validate input meat alarm warm temp range | 2017-08-30 |  | 2017-10-19
Edit cook information
|  | Change cook name | 2017-08-30 |  | 2017-10-19
|  | Change notes | 2017-08-30 |  | 2017-10-19
View cook history
|  | If end time is on next day, add (+1 day) like: JUN 03 FRI 8:17AM - 4:00PM (+1 day) |  | RC: add issue - see Home tab issue | 2017-10-19 | Issue 439 - Delivery
|  | Otherwise if controller name is set by user: cook begin-end date/time on user-controller-name | 2017-08-30 |  | 2017-10-19
|  | Otherwise cook begin-end date/time on controller # | 2017-08-30 |  | 2017-10-19
|  | Ordered by date most recent first | 2017-08-30 |  | 2017-10-19
|  | Show if notes are available | 2017-08-30 |  |  | Issue 571
|  | Offer way to delete cooks | 2017-08-30 |  | 2017-10-19
|  | Nav to view cook | 2017-08-30 |  | 2017-10-19
Receive notices
|  | New cook started |  | Did not receive a notification | NO | Did not receive a notification
|  | Pit temp out of normal range |  | Did not receive a notification | NO | Did not receive a notification
|  | Meat done |  | Did not receive a notification | NO | Did not receive a notification
|  | User added controller |  | Did not receive a notification | NO | Did not receive a notification
Note on A1: Add any entries from v1 -Roger Collins

## later
Section/Use Case |  | Date Verified | Comments
Requirement
Deployment
| Build and distribute through TestFlight | 2017-06-24
Navigation/General
Runs on iPhone
Runs on iPad
Runs on iPhone in portrait mode
Runs on iPhone in landscape mode
Runs on iPad in portrait mode
Runs on iPad in landscape mode
App icon
Loading image
| Show login/signup/skip option until first successful login, successful signup, or skip | 2017-06-07 | Verified by Kevoye
Show phone offline state when phone cannot communicate with server or controller
Navigation tabs
Home
Controller
History
Account
Fails gracefully when cannot connect to server
About?
Terms & Conditions
Link to FlameBoss.com
Link to web app myflameboss.com
Link to Facebook page
Home
Shown on home tab
The first view on app open
Input device ID
Button to view most-recent-cook on input device ID
Handle invalid device ID
Handle no-cook-yet on valid device ID
Use user-assigned names for controllers
View added-controllers most recent cooks
View local-network most recent cooks
View added-controllers before local-network
Cook list entries nav to view cook
If end time is on next day, add (+1 day) like: JUN 03 FRI 8:17AM - 4:00PM (+1 day)
Setup wifi with AP mode
Popup dialog to start if no devices in index (either IP or added)
Can also start from controllers tab
Wizard style steps
Cancellation/abort available at any time
Instructs to put controller in AP Mode
Instructs to join controller network
Instructs to re-open app
Shows when connected to Flame Boss
Shows networks visible to controller for selection
Inputs password, hidden by default
Show password option
App detects controller online
Instructs to find PIN on controller
Inputs PIN
Adds controller to users profile
Add a controller
Input Device ID
Input PIN
Input SN (optional)
Validate SN is 6 or 7 digit number
Controller settings
Controller name
Easy to find in navigation
Input name
Wifi settings
Scanned wifi settings
Easy to find in navigation
View SSID
View security type
Cannot view password
SSID choices from controller
Input password, hidden by default
Show password option (while inputting)
Manual wifi settings
Input SSID (not shown in choices from controller)
Input password, hidden by default
Show password option (while inputting)
Input wifi security type
Sound
View current sound setting
Change sound setting
No sound, chirps only, or chirps and alarms
Edit controller name
Account
Sign up
Input email
Input email with email keypad
Input username
Input username default lowercase
Input phone
Input phone with phone keypad
Input texts notices enabled
Input temperature scale
Default temperature scale by device locale
Login
Use email or username
Secure password entry
Handle incorrect pw
| Handle lockout too many tries |  | I was able to log in the 27th time after 26 attempts with the wrong password.
Logout
View/edit user profile
View username
View email
View mobile phone number
View text confirmation status of phone number
Input text confirmation code only if we sent a code and it is not confirmed yet
View texts enabled option
View preferred temp scale
Change email
Validate email
Use email keypad for email input
Change mobile phone number
Validate mobile phone number
Use keypad for phone number input
Change texts enabled option
Change preferred temp scale
View cook
Back control navigates to previous view
User-assigned title used if set
View pit temp, meat temps, and blower output
View graph of temps and blower output over time
Share link on myflameboss.com
Share on twitter
Reference FB's twitter username
Share on facebook
Reference Flame Boss's facebook username
View set temp
Change set temp
Show valid range for set temp
Validate input set temp range: on error, show (again) range required, allow cancel
Show activity indicator until response from server, timeout 10 sec: change phone to offline
View pit alarm
Change pit alarm
| Validate input pit alarm range: on error, show (again) range required, allow cancel |  | No feedback is given regardless of what is entered.
View meat alarm done temp
Change meat alarm done temp
Validate input meat alarm done temp range
View meat alarm warm temp
Change meat alarm warm temp
Validate input meat alarm warm temp range
Edit cook information
Change cook name
Change notes
View cook history
If end time is on next day, add (+1 day) like: JUN 03 FRI 8:17AM - 4:00PM (+1 day)
Otherwise if controller name is set by user: cook begin-end date/time on user-controller-name
Otherwise cook begin-end date/time on controller #
Ordered by date most recent first
Show if notes are available
Offer way to delete cooks
Nav to view cook
Receive notices
New cook started
Pit temp out of normal range
Meat done
User added controller
Note on A1: Add any entries from v1 -Roger Collins

## status
Requirements | 133
Verified | 99
Verified % | 74.44%